## ACTIVITY TIMELINE YEAR 1
PLACEHOLDER FOR COUNTRY OFFICE BRAND/LOGO
YEAR
ACTIVITY | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FUNDRAISING, TEAM BUILDING, PROTOCOL FINALIZATION, ETHICS APPROVAL
Draft concept note/proposal and other documents to support fundraising efforts for the survey
Secure funding for the survey
Identify key partnerships and establish survey governance and any institutional agreements
Conduct national technical/partnership meeting(s) to begin outlining survey design and implementation decisions
Conduct national technical/partnership meeting(s) to finalize survey design and implementation decisions
Draft survey instruments, including questionnaires and informed consent forms
Complete detailed survey protocol
Complete budget for all survey activities
Obtain ethics approval for survey
Recruit key technical personnel who will engage in detailed preparatory survey activities below
COMPILE COMPREHENSIVE FOOD, RECIPE AND INGREDIENT LISTING FOR TARGET GROUPS AND GEOGRAPHIC AREAS OF FOCUS FOR THE SURVEY
Compile initial Food, Recipe and Ingredient Listing from secondary data sources for target groups and geographic areas of focus
Engage with experts and key informants to update, expand, and add details and codes to the initial Food, Recipe and Ingredient Listing. If a codelist from an existing food composition table for the country is available, this can be used as a starting point for the coding; and expanded or revised, as necessary, with FoodEx2 codes, and in accordance with any planned data capture software. The codelist will be the basis for the food composition database to be developed and used for the survey.
Summarize the Food, Recipe and Ingredient Listing data; Prioritize and select "standard" recipes to collect
Conduct facilitated group interviews to close any remaining gaps in the Food, Recipe and Ingredient Listing (include time for training of field teams and the selection and mobilization of sites and participants )
Conduct informal market surveys in urban/peri urban areas to collect data on the processed packaged and processed prepared foods consumed to further inform the Food, Recipe and Ingredient Listing (include time for training of field teams and the selection and mobilization of sites)
Finalize the Food, Recipe and Ingredient Listing, with the necessary level of detail and coding
PREPARE AND TRANSLATE ALL FIELD TOOLS, PRE-TEST PORTION SIZE ESTIMATION METHODS, PROCURE FIELD EQUIPMENT AND SUPPLIES
Prepare the "Probe List" for the survey. The Probe List is a detailed list of probes and prompts for all the different foods, recipes, and ingredients included in the Food, Recipe and Ingredient Listing.
Develop the "Food Measurement List" for the survey. The Food Measurement List is the list of approved portion size estimation methods to use for each food, recipe, and ingredient included in the Food, Recipe and Ingredient Listing.
Elaborate a protocol, and develop and validate a graduated photo series for portion size estimation of selected foods, if relevant
Conduct a field pre-testing (and/or validation) of all portion size estimation methods to be used in the survey
Procure equipment needed for all phases of the survey
Translate the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary
COMPILE THE DATABASES REQUIRED FOR CONVERTING DIETARY DATA INTO NUTRIENT INTAKES, ADAPT DATA CAPTURE SOFTWARE
Finalize the food composition database to be used for the survey based on the comprehensive Food, Recipe and Ingredients Listing and the resulting codelist
Compile the initial gram weight conversion databases from secondary sources (e.g. previous national, regional and international publications and databases)
Elaborate field protocols and tools for the field collection of standard recipes and any missing gram weight conversion factors
Train for collecting "standard recipes" and any missing gram weight conversion factors
Collect data for "standard recipes" and any missing gram weight conversion factors
Finalize the gram weight conversion database
Finalize the "standard" recipe database
Upload all databases, test/re-test and adapt data capture/entry software (if tablets will be used for data collection)
PREPRATIONS FOR TRAINING AND RECRUITMENT OF FIELD STAFF
Develop training slides, pre-training guides, and field standard operating procedures to guide data collection for the survey
Prepare training modules for data capture software (if tablets will be used for data collection)
Prepare detailed training program schedule and book training venues
Assemble all training materials and equipment for the survey, including any data capture hardware and software that will be used
Recruit and select all field staff according to the survey field team structure
TRAINING OF SURVEY STAFF, PRE-TESTING, PILOT-TESTING, AND REVISION OF ALL SURVEY TOOLS AND TRANSLATIONS, AS NEEDED
Conduct Trainer of Trainers (TOT) training (e.g. for field coordinators and supervisors) ahead of the main training for enumerators
Review all translations of the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools with field coordinators and supervisors as part of TOT training
Update all translated survey tools as necessary based on input from the field coordinators and supervisors as part of TOT training
Pre-test all survey tools as part of TOT training
Review and revise all survey tools (including data capture software, if relevant) and procedures, as necessary, based on pre-testing as part of TOT training
Provide re-training to Trainers (e.g. to field coordinators and supervisors) for any revised tools, procedures, and methods
Conduct main training workshop for all field staff (e.g. enumerators, respondent pre-trainers, data entry operators (if paper questionnaires will be used for data collection), and community mobilizers)
Refine translations of the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary, based on input from field staff during training
Conduct field pilot surveys followed by data entry
Review and revise all tools (including data capture software, if relevant) and procedures, as necessary, based on pilot surveys. Update any translations on the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary, based on the pilot surveys.
Provide retraining to all field staff for any revised tools, procedures, and methods
CLUSTER SELECTION, COMMUNITY MOBILIZATION AND SENSITIZATION, HOUSEHOLD ENUMERATION WITHIN CLUSTERS, RESPONDENT SELECTION
Create sampling frames and select clusters to be sampled
Conduct project introduction visits at all administrative and community levels, obtain relevant permissions
Conduct training for carrying out census of households in clusters
Conduct household enumeration in selected clusters (map households), complete household roster at all households to identify eligible respondents at each household within the cluster (if relevant and not using a household-based sampling methodology), select respondents to participate in the survey
DATA COLLECTION PHASE
Finalize survey team selection, and contracting of all survey staff
Ensure all necessary local permissions have been obtained
Create a tentative data collection schedule for each survey team
Finalize logistic arrangements for the survey (including field team transportation and accommodation)
Re-mobilize survey area communities, as needed
Deploy teams and carry out respondent pre-training (if applicable)
Collect dietary data and implement field supervision, data quality control, and appropriate communication procedures across enumeration teams to ensure new foods and situations are addressed in a standardized way during data collection
DATA ENTRY AND PROCESSING
Prepare computers and create/upload software needed for data entry (if paper questionnaires will be used for data collection)
Conduct specialized training for data entry staff on software/data entry program to be used (if paper questionnaires will be used for data collection)
Double-enter all survey data. Review differences in double-entered data and reconcile the differences. Document and make corrections to the data entered, as needed. Conduct quality control checks on data entry (if paper questionnaires will be used for data collection).
Identify all foods/ingredients/recipes arising in the survey data that are missing from the food composition database for the survey. Identify or collect any additional information needed to complete dietary data entry and processing. Reprocess final dietary data with any updated input data and export final dietary data reports.
Clean dietary intake data, examining high and low intakes, implausible intakes for foods and energy/nutrients. Generate final clean datasets.
DATA ANALYSIS AND TECHNICAL REPORTING AND DISSEMINATION
Develop a data analysis plan, report structure, and table shells
Prepare summary statistics for food intakes, energy and nutrient intakes, and conduct data analysis to respond to survey objectives
Prepare a final report and interpretation of the results
Disseminate results, and translate findings for use by various audiences and stakeholders

## ACTIVITY TIMELINE YEAR 2
PLACEHOLDER FOR COUNTRY OFFICE BRAND/LOGO
YEAR
ACTIVITY | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FUNDRAISING, TEAM BUILDING, PROTOCOL FINALIZATION, ETHICS APPROVAL
Draft concept note/proposal and other documents to support fundraising efforts for the survey
Secure funding for the survey
Identify key partnerships and establish survey governance and any institutional agreements
Conduct national technical/partnership meeting(s) to begin outlining survey design and implementation decisions
Conduct national technical/partnership meeting(s) to finalize survey design and implementation decisions
Draft survey instruments, including questionnaires and informed consent forms
Complete detailed survey protocol
Complete budget for all survey activities
Obtain ethics approval for survey
Recruit key technical personnel who will engage in detailed preparatory survey activities below
COMPILE COMPREHENSIVE FOOD, RECIPE AND INGREDIENT LISTING FOR TARGET GROUPS AND GEOGRAPHIC AREAS OF FOCUS FOR THE SURVEY
Compile initial Food, Recipe and Ingredient Listing from secondary data sources for target groups and geographic areas of focus
Engage with experts and key informants to update, expand, and add details and codes to the initial Food, Recipe and Ingredient Listing. If a codelist from an existing food composition table for the country is available, this can be used as a starting point for the coding; and expanded or revised, as necessary, with FoodEx2 codes, and in accordance with any planned data capture software. The codelist will be the basis for the food composition database to be developed and used for the survey.
Summarize the Food, Recipe and Ingredient Listing data; Prioritize and select "standard" recipes to collect
Conduct facilitated group interviews to close any remaining gaps in the Food, Recipe and Ingredient Listing (include time for training of field teams and the selection and mobilization of sites and participants )
Conduct informal market surveys in urban/peri urban areas to collect data on the processed packaged and processed prepared foods consumed to further inform the Food, Recipe and Ingredient Listing (include time for training of field teams and the selection and mobilization of sites)
Finalize the Food, Recipe and Ingredient Listing, with the necessary level of detail and coding
PREPARE AND TRANSLATE ALL FIELD TOOLS, PRE-TEST PORTION SIZE ESTIMATION METHODS, PROCURE FIELD EQUIPMENT AND SUPPLIES
Prepare the "Probe List" for the survey. The Probe List is a detailed list of probes and prompts for all the different foods, recipes, and ingredients included in the Food, Recipe and Ingredient Listing.
Develop the "Food Measurement List" for the survey. The Food Measurement List is the list of approved portion size estimation methods to use for each food, recipe, and ingredient included in the Food, Recipe and Ingredient Listing.
Elaborate a protocol, and develop and validate a graduated photo series for portion size estimation of selected foods, if relevant
Conduct a field pre-testing (and/or validation) of all portion size estimation methods to be used in the survey
Procure equipment needed for all phases of the survey
Translate the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary
COMPILE THE DATABASES REQUIRED FOR CONVERTING DIETARY DATA INTO NUTRIENT INTAKES, ADAPT DATA CAPTURE SOFTWARE
Finalize the food composition database to be used for the survey based on the comprehensive Food, Recipe and Ingredients Listing and the resulting codelist
Compile the initial gram weight conversion databases from secondary sources (e.g. previous national, regional and international publications and databases)
Elaborate field protocols and tools for the field collection of standard recipes and any missing gram weight conversion factors
Train for collecting "standard recipes" and any missing gram weight conversion factors
Collect data for "standard recipes" and any missing gram weight conversion factors
Finalize the gram weight conversion database
Finalize the "standard" recipe database
Upload all databases, test/re-test and adapt data capture/entry software (if tablets will be used for data collection)
PREPRATIONS FOR TRAINING AND RECRUITMENT OF FIELD STAFF
Develop training slides, pre-training guides, and field standard operating procedures to guide data collection for the survey
Prepare training modules for data capture software (if tablets will be used for data collection)
Prepare detailed training program schedule and book training venues
Assemble all training materials and equipment for the survey, including any data capture hardware and software that will be used
Recruit and select all field staff according to the survey field team structure
TRAINING OF SURVEY STAFF, PRE-TESTING, PILOT-TESTING, AND REVISION OF ALL SURVEY TOOLS AND TRANSLATIONS, AS NEEDED
Conduct Trainer of Trainers (TOT) training (e.g. for field coordinators and supervisors) ahead of the main training for enumerators
Review all translations of the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools with field coordinators and supervisors as part of TOT training
Update all translated survey tools as necessary based on input from the field coordinators and supervisors as part of TOT training
Pre-test all survey tools as part of TOT training
Review and revise all survey tools (including data capture software, if relevant) and procedures, as necessary, based on pre-testing as part of TOT training
Provide re-training to Trainers (e.g. to field coordinators and supervisors) for any revised tools, procedures, and methods
Conduct main training workshop for all field staff (e.g. enumerators, respondent pre-trainers, data entry operators (if paper questionnaires will be used for data collection), and community mobilizers)
Refine translations of the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary, based on input from field staff during training
Conduct field pilot surveys followed by data entry
Review and revise all tools (including data capture software, if relevant) and procedures, as necessary, based on pilot surveys. Update any translations on the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary, based on the pilot surveys.
Provide retraining to all field staff for any revised tools, procedures, and methods
CLUSTER SELECTION, COMMUNITY MOBILIZATION AND SENSITIZATION, HOUSEHOLD ENUMERATION WITHIN CLUSTERS, RESPONDENT SELECTION
Create sampling frames and select clusters to be sampled
Conduct project introduction visits at all administrative and community levels, obtain relevant permissions
Conduct training for carrying out census of households in clusters
Conduct household enumeration in selected clusters (map households), complete household roster at all households to identify eligible respondents at each household within the cluster (if relevant and not using a household-based sampling methodology), select respondents to participate in the survey
DATA COLLECTION PHASE
Finalize survey team selection, and contracting of all survey staff
Ensure all necessary local permissions have been obtained
Create a tentative data collection schedule for each survey team
Finalize logistic arrangements for the survey (including field team transportation and accommodation)
Re-mobilize survey area communities, as needed
Deploy teams and carry out respondent pre-training (if applicable)
Collect dietary data and implement field supervision, data quality control, and appropriate communication procedures across enumeration teams to ensure new foods and situations are addressed in a standardized way during data collection
DATA ENTRY AND PROCESSING
Prepare computers and create/upload software needed for data entry (if paper questionnaires will be used for data collection)
Conduct specialized training for data entry staff on software/data entry program to be used (if paper questionnaires will be used for data collection)
Double-enter all survey data. Review differences in double-entered data and reconcile the differences. Document and make corrections to the data entered, as needed. Conduct quality control checks on data entry (if paper questionnaires will be used for data collection).
Identify all foods/ingredients/recipes arising in the survey data that are missing from the food composition database for the survey. Identify or collect any additional information needed to complete dietary data entry and processing. Reprocess final dietary data with any updated input data and export final dietary data reports.
Clean dietary intake data, examining high and low intakes, implausible intakes for foods and energy/nutrients. Generate final clean datasets.
DATA ANALYSIS AND TECHNICAL REPORTING AND DISSEMINATION
Develop a data analysis plan, report structure, and table shells
Prepare summary statistics for food intakes, energy and nutrient intakes, and conduct data analysis to respond to survey objectives
Prepare a final report and interpretation of the results
Disseminate results, and translate findings for use by various audiences and stakeholders

## ACTIVITY TIMELINE YEAR 3
PLACEHOLDER FOR COUNTRY OFFICE BRAND/LOGO
YEAR
ACTIVITY | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FUNDRAISING, TEAM BUILDING, PROTOCOL FINALIZATION, ETHICS APPROVAL
Draft concept note/proposal and other documents to support fundraising efforts for the survey
Secure funding for the survey
Identify key partnerships and establish survey governance and any institutional agreements
Conduct national technical/partnership meeting(s) to begin outlining survey design and implementation decisions
Conduct national technical/partnership meeting(s) to finalize survey design and implementation decisions
Draft survey instruments, including questionnaires and informed consent forms
Complete detailed survey protocol
Complete budget for all survey activities
Obtain ethics approval for survey
Recruit key technical personnel who will engage in detailed preparatory survey activities below
COMPILE COMPREHENSIVE FOOD, RECIPE AND INGREDIENT LISTING FOR TARGET GROUPS AND GEOGRAPHIC AREAS OF FOCUS FOR THE SURVEY
Compile initial Food, Recipe and Ingredient Listing from secondary data sources for target groups and geographic areas of focus
Engage with experts and key informants to update, expand, and add details and codes to the initial Food, Recipe and Ingredient Listing. If a codelist from an existing food composition table for the country is available, this can be used as a starting point for the coding; and expanded or revised, as necessary, with FoodEx2 codes, and in accordance with any planned data capture software. The codelist will be the basis for the food composition database to be developed and used for the survey.
Summarize the Food, Recipe and Ingredient Listing data; Prioritize and select "standard" recipes to collect
Conduct facilitated group interviews to close any remaining gaps in the Food, Recipe and Ingredient Listing (include time for training of field teams and the selection and mobilization of sites and participants )
Conduct informal market surveys in urban/peri urban areas to collect data on the processed packaged and processed prepared foods consumed to further inform the Food, Recipe and Ingredient Listing (include time for training of field teams and the selection and mobilization of sites)
Finalize the Food, Recipe and Ingredient Listing, with the necessary level of detail and coding
PREPARE AND TRANSLATE ALL FIELD TOOLS, PRE-TEST PORTION SIZE ESTIMATION METHODS, PROCURE FIELD EQUIPMENT AND SUPPLIES
Prepare the "Probe List" for the survey. The Probe List is a detailed list of probes and prompts for all the different foods, recipes, and ingredients included in the Food, Recipe and Ingredient Listing.
Develop the "Food Measurement List" for the survey. The Food Measurement List is the list of approved portion size estimation methods to use for each food, recipe, and ingredient included in the Food, Recipe and Ingredient Listing.
Elaborate a protocol, and develop and validate a graduated photo series for portion size estimation of selected foods, if relevant
Conduct a field pre-testing (and/or validation) of all portion size estimation methods to be used in the survey
Procure equipment needed for all phases of the survey
Translate the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary
COMPILE THE DATABASES REQUIRED FOR CONVERTING DIETARY DATA INTO NUTRIENT INTAKES, ADAPT DATA CAPTURE SOFTWARE
Finalize the food composition database to be used for the survey based on the comprehensive Food, Recipe and Ingredients Listing and the resulting codelist
Compile the initial gram weight conversion databases from secondary sources (e.g. previous national, regional and international publications and databases)
Elaborate field protocols and tools for the field collection of standard recipes and any missing gram weight conversion factors
Train for collecting "standard recipes" and any missing gram weight conversion factors
Collect data for "standard recipes" and any missing gram weight conversion factors
Finalize the gram weight conversion database
Finalize the "standard" recipe database
Upload all databases, test/re-test and adapt data capture/entry software (if tablets will be used for data collection)
PREPRATIONS FOR TRAINING AND RECRUITMENT OF FIELD STAFF
Develop training slides, pre-training guides, and field standard operating procedures to guide data collection for the survey
Prepare training modules for data capture software (if tablets will be used for data collection)
Prepare detailed training program schedule and book training venues
Assemble all training materials and equipment for the survey, including any data capture hardware and software that will be used
Recruit and select all field staff according to the survey field team structure
TRAINING OF SURVEY STAFF, PRE-TESTING, PILOT-TESTING, AND REVISION OF ALL SURVEY TOOLS AND TRANSLATIONS, AS NEEDED
Conduct Trainer of Trainers (TOT) training (e.g. for field coordinators and supervisors) ahead of the main training for enumerators
Review all translations of the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools with field coordinators and supervisors as part of TOT training
Update all translated survey tools as necessary based on input from the field coordinators and supervisors as part of TOT training
Pre-test all survey tools as part of TOT training
Review and revise all survey tools (including data capture software, if relevant) and procedures, as necessary, based on pre-testing as part of TOT training
Provide re-training to Trainers (e.g. to field coordinators and supervisors) for any revised tools, procedures, and methods
Conduct main training workshop for all field staff (e.g. enumerators, respondent pre-trainers, data entry operators (if paper questionnaires will be used for data collection), and community mobilizers)
Refine translations of the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary, based on input from field staff during training
Conduct field pilot surveys followed by data entry
Review and revise all tools (including data capture software, if relevant) and procedures, as necessary, based on pilot surveys. Update any translations on the questionnaire and data collection forms, the Food, Recipe and Ingredients Listing, the Probe List, the Food Measurement List, and any other survey tools, as necessary, based on the pilot surveys.
Provide retraining to all field staff for any revised tools, procedures, and methods
CLUSTER SELECTION, COMMUNITY MOBILIZATION AND SENSITIZATION, HOUSEHOLD ENUMERATION WITHIN CLUSTERS, RESPONDENT SELECTION
Create sampling frames and select clusters to be sampled
Conduct project introduction visits at all administrative and community levels, obtain relevant permissions
Conduct training for carrying out census of households in clusters
Conduct household enumeration in selected clusters (map households), complete household roster at all households to identify eligible respondents at each household within the cluster (if relevant and not using a household-based sampling methodology), select respondents to participate in the survey
DATA COLLECTION PHASE
Finalize survey team selection, and contracting of all survey staff
Ensure all necessary local permissions have been obtained
Create a tentative data collection schedule for each survey team
Finalize logistic arrangements for the survey (including field team transportation and accommodation)
Re-mobilize survey area communities, as needed
Deploy teams and carry out respondent pre-training (if applicable)
Collect dietary data and implement field supervision, data quality control, and appropriate communication procedures across enumeration teams to ensure new foods and situations are addressed in a standardized way during data collection
DATA ENTRY AND PROCESSING
Prepare computers and create/upload software needed for data entry (if paper questionnaires will be used for data collection)
Conduct specialized training for data entry staff on software/data entry program to be used (if paper questionnaires will be used for data collection)
Double-enter all survey data. Review differences in double-entered data and reconcile the differences. Document and make corrections to the data entered, as needed. Conduct quality control checks on data entry (if paper questionnaires will be used for data collection).
Identify all foods/ingredients/recipes arising in the survey data that are missing from the food composition database for the survey. Identify or collect any additional information needed to complete dietary data entry and processing. Reprocess final dietary data with any updated input data and export final dietary data reports.
Clean dietary intake data, examining high and low intakes, implausible intakes for foods and energy/nutrients. Generate final clean datasets.
DATA ANALYSIS AND TECHNICAL REPORTING AND DISSEMINATION
Develop a data analysis plan, report structure, and table shells
Prepare summary statistics for food intakes, energy and nutrient intakes, and conduct data analysis to respond to survey objectives
Prepare a final report and interpretation of the results
Disseminate results, and translate findings for use by various audiences and stakeholders